## Items needed 4th 2019
Activity/Item | What's needed | Who's Responsible
Pop Ring Toss | 75 2 liters | Brian Wright - will drop off on the 3rd evening
| small prize box | Emma - will create with teenage helpers
| black sharpie | Jenny will bring
| plastic rings | in storage room
| flat pieces of wood from storage room | in storage room
| volunteer description | Jenny
Ball pool game | plastic balls | in storage room
| blow up pool | in storage room
| Black and red sharpie | Jenny will bring
| small prize box | Emma - will create with teenage helpers
| volunteer description | Jenny
| individual food snacks | Emma
Plinko | Plinko game | in storage room
| Plinko wooden chips | should be on the Plinko game
| small prize box | Emma - will create with teenage helpers
| individual food snacks | Emma
| volunteer description | Jenny
Drink Sales | 100 bottles of water | Brian Wright - will drop off on the 3rd evening
| 50 cans of lemonade | Brian Wright - will drop off on the 3rd evening
| large open tubs for ice/drinks | in storage room
| ice (to go in freezer) | someone needs to buy on the 3rd and put in freezer
| signs advertising prices | AJ will print on colored paper
| cash box | Jenny will obtain from Dave
| volunteer description | Jenny
Wristband Sales | two supply boxes made for wristband sellers | Jenny
| wristbands | Jenny will put in boxes
| volunteer description | Jenny
| signs advertising prices | Emily Castle making 3 signs
| Pop up tent | One tent needed for 2nd ticket sales station - Jenny will p/u on the 3rd
| Cash boxes | Jenny will obtain from Dave
Craft tables | craft supplies | AJ
| craft example | AJ
| volunteer description | AJ
| sign advertisting the craft event | needs to be made
Watermelon contest | watermelon | Brian Wright - will drop off on the 3rd evening
| knife to cut the morning of the 4th | AJ
| prizes for the 3 competitions | AJ
| wet wipes/napkins | AJ
| sign advertising the events and times of competitions | needs to be made
| plates for the sliced watermelon | AJ
| serving tray to carry out watermelon slices | AJ
| cutting tray | AJ
| volunteer description | AJ
Pie Judging Competition | Sign for pie makers to identify their pie and provide their contact info in shelter house | AJ
| plates for sliced pies (identified with a # per pie) | AJ
| pie slicer | AJ
| score cards for judges | AJ
| serving tray to bring out the pies to judges | AJ
| forks and napkins for judges | AJ
| prize for winner | AJ
| sign advertising event | needs to be made
Face painters | sign advertising event | needs to be made
Small prize bag for all children | bags compiled | Emma
| sign to let kids know to take one for free | needs to be made
Bubble pop game | one tent | Alan will pick up on the 3rd
| sign advertising event | needs to be made
Musician | one tent | Alan will pick up on the 3rd
| sign thanking musician | needs to be made
Ron's games | one tent | Alan will pick up on the 3rd
two tables
4 chairs
Slip & Slide | One chair
sign defining rules
Dunk Tank | chair
sign defining rules
Small bounce house | chair
sign defining rules

## AJ to print
Sign for: | Wording: | # Needed
Drink table | Suggested donation of $1.00 per drink - honor system for payment. Bottled water and lemonade options only. | 2
Craft table | Patriotric Crafts - fun for all ages | 2
Pie bakers |  | 1 | Thoughts on wording: CH pie bakers - please leave your pie on the counter in the kitchen. Please place a numbered card on your pie (or tape to the pie box). Then please fill out a notecard, indicate your pie number as well as your full name, email address and phone number. Please this card (with your number) into the box below to remain anonymous to the judges. You will be notified after the event if you won.

## Volunteer Shifts
Date | Volunteer Start time | Volunteer End Time | Activity | Person filling position
3rd | 6:00 | 20:00 | *Set up support
3rd | 6:00 | 20:00 | *Set up support
3rd | 6:00 | 20:00 | *Set up support
4th | 8:30 | 10:30AM | *Set up support
4th | 8:30 | 10:30AM | *Set up support
4th | 8:30 | 10:30 | *Set up support
4th | 10:15 | 12:00 | *Runner / Misc
4th | 10:15 | 12:45 | *Ticket Sales
4th | 10:15 | 12:45 | *Ticket Sales
4th | 10:15 | 12:45 | *Ticket Sales
4th | 10:15 | 12:45 | *Ticket Sales
4th | 10:15 | 12:00 | *Beverage Sales
4th | 10:15 | 12:00 | *Toddler bounce house
4th | 10:15 | 12:00 | Magniko
4th | 10:15 | 12:00 | *Slip & Slide
4th | 10:15 | 12:00 | *Dunk tank
4th | 10:15 | 11:30 | Pie judging volunteer
4th | 10:15 | 12:00 | Pop Ring Toss
4th | 10:15 | 12:00 | Craft table volunteer
4th | 10:15 | 12:00 | Ball pool
4th | 10:15 | 12:00 | Plinko
4th | 11:30 | 13:00 | Watermelon contest volunteer
4th | 12:00 | 13:30 | *Beverage Sales
4th | 12:00 | 13:30 | *Runner / Misc
4th | 12:00 | 13:30 | *Toddler bounce house
4th | 12:00 | 13:30 | Magniko
4th | 12:00 | 13:30 | *Slip & Slide
4th | 12:00 | 13:30 | *Dunk tank
4th | 12:00 | 13:30 | Craft table volunteer
4th | 12:00 | 13:30 | Pop Ring Toss
4th | 12:00 | 13:30 | Ball pool
4th | 12:00 | 13:30 | Plinko
4th | 13:00 | 14:00 | *Take-down support
4th | 13:00 | 14:00 | *Take-down support
4th | 13:00 | 14:00 | Take-down support
4th | 13:00 | 14:00 | Take-down support
* = adult volunteer

## Signs needed 2019
Activity | Wording for Sign | Details | Homemade or purchased
ticket sales | $5 wristband allows access to all activities | Front and back, 3 signs, yellow with black lettering | purchased (Jenny has already Emily Castle to make)
Craft table | Craft table under big top - fun for all | Front, 2 signs | homemade
Watermelon competition | Watermelon eating competition under big top: 11:45 under 18, 12:15 adults, 12:45 under 18 | Front, 2 signs | homemade
Pie judging competition | Pie Judging Competition - all pies in shelter house by 10:30, judging begins at 11:00 under big top | Front, 2 signs | homemade
Small prize bag | Free - please enjoy a bag of small 4th of July prizes. One bag per child. | Front only - can be taped on table | homemade
Musician | Thanks to our own talented Matt Steidle for sharing his gift of music with us today | Front - one sign | homemade
Face painters | One item painted per child, requires a wristband unless 3 and under | Front, one sign | homemade
Dunk Tank | Emma - TBD on your preference | line up of teachers who are going to be in the tank at what time? | homemade
Slip and Slide | Emma - TBD on your preference | Maybe something about safety - one child at a time? Must be older than ??? Shoes off??? | homemade
Toddler Bounce house | Emma - TBD on your preference | Can't use old signs (as it references tickets) but probably should say "Children (some age) and under only" Please remove shoes" | homemade
Magniko | Emma - TBD based on what Ron Sears wants |  | homemade
Bubble Whack | Emma- TBD based on what Ron Sears wants |  | homemade

## To Do Tasks
Activity | Date | Who | Details | Completed
Order bounce house, dunk tank, Slip & Slide & face painters from Cool Cats |  | AJ | AJ ordered - AJ will call on the 3rd to ask (beg) that we be their first drop
Confirm Kona Icee truck |  | AJ | Confirm attendance and pricing from 10:30-12:30 on the 4th. AJ will need to contact to ensure they remember to come down N Selby and call when they hit a barricade. The runner/barricade person must clear the road and driveway to bring them in.
Confirm sponsorship of Kona truck by CyMack | Fall of 2018 | Jenny | CyMack paid in the fall of 2018 for all 2019 events sponsored by her
Reserve shelter house with the Parks & Rec dept | Jan, 2019 | Jenny | Need shelter house from 8:00 am on the 3rd - 6:00 pm on the 5th. This includes both evenings - all night on the 3rd and 4th. | done in January -sent to Julie
Confirm food truck - Kenny's Meat Wagon | Spring, 2019 | AJ | Confirm Kenny from 10-1:00 on the 4th | AJ confirmed already - he's good to go. Will need a reminder to come down N Selby - not S Selby
Parade support - what is needed? | Spring, 2019 | Jenny | bulll horn which MaryAnn took home already | per MaryAnne - she has this covered
Barricades for kiddie parade | Spring, 2019 | Jenny | Check with Jeff and Courtney to see if they are ordering or should I | 6/17 - Jenny reserved barricades and conesn (8 barricades, 10 cones) 6/27 - gentleman from the parks and rec called - Courtney placed a larger order and JK agreed to just use theirs
Check in with 5K race leaders | Spring, 2019 | Jenny | Contact Jeff Spain/Courtney Jolly to ensure all are on the same schedule - race still at 8:30, we will start the parade at 10, midway at 10:30, they will order port o potties which will be placed on S side of shelter house facing S Selby - Jenny confirmed with the company during pick up in 2018 that they can place on the S side of building. | 6/10- Jenny emailed Courtney- will follow up again 6/27 - JK gave Jeff the start up funds and have confirmed all other items
Order tents, tables and chairs | Spring, 2019 | Jenny | Jenny revised the order for less tables and chairs and provided cell # for delivery on the 3rd and pick up on the 5th.
Dumpster order with the city | Spring, 2019 | Jenny | Jenny confirmed with Julie that the city will have a dumpster there on/by the 3rd.
Create volunteer schedule/needs | Spring, 2019 | Jenny | Will create a master list of volunteer needs encompassing the 3rd and 4th | Alan completed, posted to FB
Notification of events/schedule in Courier | Spring, 2019 | AJ | See tab on this spreadsheet for volunteer needs | included in May Courier which was distribute week of 6/3
Review existing signs for the 4th - determine what needs to be ordered | Spring, 2019 | Jenny | Using the list of all activities, ensure there is a sign for each | Emma will make new signs that are needed - list on this spreadsheet
Recruit photographer for event | Spring, 2019 | Emma | We haven't had one for two years but it would be nice to see if anyone would be willing to do this | 6/27 - Emma recruited one
Order recycling bins | June, 2019 | Jenny | Order rectangular cardboard recycling tubs from Amazon or wherever - maybe 4-6 to spread throughout the park | Ordered/received/giving to Emma on 6/11 to put in storage room
Cardboard trash containers | June, 2019 | Jenny | Contacted Scott Brown, he will drop some off at shelter house on the 3rd
Create survey for volunteer needs and post on Facebook | June, 2019 |  | Using volunteer openings created above, generate a survey that aligns to these needs | Alan completed, posted to FB
Create a Facebook event | June, 2019 |  | Create on CH Facebook page | Alan completed, posted to FB
Create/print descriptor for each of the volunteer activities | June, 2019 | Jenny | See list of these from 2018, make changes and create new ones for any new volunteer positions. Examples include a descriptor for the wristband sellers, the runner/barricades position, set up positions, etc. | done for almost all (minus new activities for this year)
Create boxes of small prizes for all midway games requiring small prizes | June, 2019 | Emma | Will need two boxes of small prizes
Create boxes of large prizes for all midway games requiring large prizes | June, 2019 | Emma | Emma buying fruit snacks and/or goldfish as the "large prizes" for the two games
Create clear ziploc baggies for each midway game | June, 2019 | Jenny | Baggies will include printed instructions, paper bag for used tickets and any other necessary items such as a permanent marker for the pop ring toss game
Develop, print and deliver letter to neighbors who face the park | June, 2019 | Will | See Will for sample letter in 2018 and work with him for distribution in 2019 | Will agreed to do this already, he delivered on 6/29/19
Purchase bottled water and lemonade for concessions | June, 2019 | Brian Wright | Requested 100 bottles of water and 50 cans of lemonade | He confirmed via FB, will drop off on the 3rd around 5/5:30 (Jenny asked Dan Bunn to come early to help unload)
Purchase 2 liters | June, 2019 | Brian Wright | 75 2 liters of random types | He confirmed via FB, will drop off on the 3rd
Purchase water melon | June, 2019 | Brian Wright | He will bring 15 good sized melons | He confirmed via FB, will drop off on the 3rd
Prepare the two wristband seller boxes | June, 2019 | Jenny | Prepare boxes for two stations - clipboard with instructions | Done in May, in tub at my house
Order one large (2x3) volunteer sign | June, 2019 | Jenny | From GraphX order a large copy of the final volunteer sign up so all volunteers can see their assigned stations on the day of the event. | Jenny ordered on 6/27 and will pick up on 7/3
Inventory control at shelter house | June, 2019 | Jenny | Ensure all items one plans to use for the 4th are still in the storage room. Some things tend to have "legs" and are not there year over year. Do this early enough in June to be able to order any missing items. | Done - everything is in there
Notify treasurer of start up cash needs | June, 2019 | Jenny | Notify treasurer of start up cash needs for the 4th to stock 4 cash boxes (1 for race, 2 for ticket sales and 1 for drink sales) We had $85 starting cash/change in each cash box in 2018 and that was sufficient. | Done - Jenny messaged with Dave about this
Craft table | June, 2019 | AJ | Confirm with AJ what is needed - glue, kids scissors, etc.?
Pie judging competition | June, 2019 | AJ | Confirm with AJ what is needed - signs for drop off, numbered plates, judges forms, etc.
Dunk tank and slip & slide water source | July, 2019 | Alan | Alan will bring necessary hoses to reach both activities | Jenny will bring a tarp for underneath the slip & slide
Pick up of pop up canopy tents | July, 2019 | Alan | Jenny will provide Alan with the names/addresses of where to pick these up | done during week of 6/26 - Alan will pick up and bring on the 3rd
Purchase 8 bags of ice for freezer | 3rd of July | Alan
Tarp for under dunk tank and slip n slide | 3rd of July | Jenny
Clean out coolers for water/lemonade | July, 2019
Bring towels for the drink servers | July, 2019
Campers overnight on the 3rd | June, 2019 | Jenny | Jenny confirmed that the Bungers are available, Jenny emailed Julie (parks & rec) on 6/14 to obtain permission. If given, Jenny will notify the police as well | 6/26 - emailed with Darren Hurley, he approved campers in the park, spoke with police and let them know of campers and requested additional drive bys