## LuminaryWorkplan
Task # | Task Name | Start Date | Start Time | End Date | End Time | Assigned To | CHCA Organizational/ Functional Responsibility | Comments/Context
5 | This is a preliminary, explanatory section of this workplan, for 2023.
For 2023, even with available influenza and RSV vaccinations and effective COVID vaccinations which generally prevent severe illnesses, the following two task enhancements to mitigate respiratory illness from the COVID-pandemic years have been retained in the workflow:
1) SignUpGenius will be used to request the optimal number of volunteers, and will specify that masks are recommended for the inside tasks. 2) There will continue to be 8 separate inside workstations, rather than the 4 pre-COVID used in 2019 and previous years.
End of preliminary section of the workplan.
10 | Inventory Leftover Supplies | 2023-10-22 | 15:00 | 2023-11-14 | 21:00 | Will Pearce | Event Chair | Inventory the leftover supplies when the Shelter House storeroom is open (e.g. during Halloween Party or Nov CHCA mtg). Enter the on-hand supplies totals into the Luminary KitAssembly worksheet, q.v.
20 | Write Courier Publicity Article | 2023-10-22 |  | 2023-11-05 |  | Will Pearce | Event Chair | 2023: Per deadline for the November Courier of 2023, by 11/5 prepare and submit full article to CHCA VP/Communications. Note: Starting in 2020, the article will include a link to the given year's SignUpGenius.
30 | Publish Courier Publicity Article | 2023-11-17 |  | 2023-11-24 |  | Kate Burgener / Chris Rule | Courier Editor / CHCA VP | 2023: The November Courier will be published subsequent to the October Courier. Edit and include Luminaries publicity article in this Courier.
40 | Update Luminary Event Workplan | 2023-10-23 |  | 2023-12-02 |  | Will Pearce | Event Chair | Before the Nov. CHCA meeting, revise (this) Luminary Event Workplan for current year changes (dates, any design/process improvements, etc.) Use this updated workplan as part of the status report at the Nov CHCA mtg. Continue to revise as necessary, until the day of the Kit Assembly event.
50 | Update Luminary KitAssembly Worksheet with Current Year's Info | 2023-10-23 |  | 2023-11-29 |  | Will Pearce | Event Chair | During November, revise the Luminary KitAssembly worksheet for any current year changes (e.g., new districts, new Trustees). Enter the totals from the storeroom inventory. Use this updated worksheet as reference for status report at Nov CHCA mtg. See Note below.
Note: The Luminary KitAssembly worksheet is the other main document besides the overall Luminary Event Workplan, and has an associated workbook, q.v., which contains instructions and notes for this worksheet: e.g., entering inventory, updating w/ Trustee info, etc. The updated Trustee info is the source for the Update Bundle Sheets task, q.v.
60 | Give Luminaries Event Status Report at Nov CHCA Mtg | 2023-11-14 | 19:30 | 2023-11-14 | 20:30 | Will Pearce | Event Chair | Give high level status review, to include all tasks to be performed before the Kits Assembly event: e.g., recruiting volunteers, letter to trustees, signage, pea gravel delivery, purchasing coffee and donuts. Usually, the November CHCA meeting will be the last before the Kit Assembly event.
70 | Recruit Specific Volunteers | 2023-11-04 |  | 2023-12-01 |  | Will Pearce / Leslie Caruso | Event Chair / CHCA President | Certain specific volunteers need to be recruited and perform tasks prior to the Kit Assembly event. Namely, a person to purchase coffee, donuts, etc. Publicity signage is also needed, and is covered as a separate task, q.v. Also, it is highly desirable, to secure a prior commitment for a Supervisor for Bundling the Kits, and for people to bring garden shovels.
80 | Purchase (or Secure Donations for) Luminary Kits Supplies | 2023-11-03 |  | 2023-11-29 |  | Will Pearce | Event Chair | No later than the week after Thanksgiving, purchase (or secure donations for) the kit supplies shown in the "Supplies To Be Purchased/Donated" column of the KitAssembly worksheet (ordering pea gravel is a separate task) New item for 2012: Buy six 1" x 2" x 36" wood garden stakes, to increase the efficiency of gravel shoveling, in stacking opened plastic grocery bags (new task 175). The Event Chair stores these stakes at home so they don't get lost. New item for 2015: Event chair will buy 4 "T-shirt" grocery sack racks, and will store these racks at home.
90 | Update the Luminary Setup Instruction Sheet for the Current Year's Info, and E-mail to Copies Plus. Note: For 2011, CopiesPlus changed its name to Graph X Productions, and moved to 6351 Nicholas Drive (down this street from Mr. Mulch). Thus, e-mail to: orders@graphxproductions.com. Note: For 2021, attach a scanned image of the Event Sponsor(s)' business card(s) to the e-mail to GraphX, along with the request to print the image(s) on the back of each instruction sheet. Note: For 2022, GraphX moved one street to the west, to: 6500 Fiesta Drive. | 2023-11-03 |  | 2023-11-27 |  | Will Pearce | Event Chair | No later than the week after Thanksgiving, update the Instruction Sheet (which is inserted in the luminary kits) for the current year's date and any other changed info. Send an e-mail with the updated Instructions Word document attached, to the CHCA President, requesting that the President review and approve. Then attach this Word document to an e-mail to Copies Plus specifying: the required number of copies (specify a few more than needed); that each page is to be cut into two copies; and that it is for the Colonial Hills Civic Association. E-mail to (rev. 2011): orders@graphxproductions.com.
95 | Count out the correct number of Luminary Setup Instruction Sheets for each "inside" workflow workstation, for use as process control during the Kit Assembly event. | 2023-11-27 |  | 2023-12-01 |  | Will Pearce | Event Chair | After picking up the Luminary Setup Instruction Sheets from the printer, but no later than the day before the Kit Assembly event, count out the correct quantities for each workstation, as described in the Kit Assembly Worksheet Instructions and Notes. 2022 & 2023, per COVID modifications: Specifically, the quantities for each of the 8 workstations will be, respectively, 100, 100, 100, 100, 100, 100, 100, (Total kits - 700).
98 | New Task for 2021: Count out the correct number of plastic grocery sacks, and place in the box to be given to the shovelers, for use as the shoveling process control. | 2023-11-27 |  | 2023-12-01 |  | Will Pearce | Event Chair | The exact number of grocery bags (the same as the number of instruction sheets) will be given to the shovelers, so that they know when they are done, and so as to prevent their creating an excess of pea gravel sacks. Also, 25 additional sacks will be counted into another box, as a contingency for broken sacks and a "fudge factor" for small miscounts in the workflow.
100 | Order Pea Gravel for Delivery | 2023-11-24 |  | 2023-11-27 |  | Will Pearce | Event Chair | At the beginning of December, but no later than one week prior to the Kit Assembly event, order pea gravel from the current vendor (which has been Mr. Mulch on W. Dublin-Granville Rd for many years), for delivery at the Selby Park shelter house, on the Friday before the event day. It is highly recommended that you go over to Mr. Mulch, and perform this ordering and delivery specification in person, exactly one week before the Friday delivery date.
110 | Write Letter to Trustees to Pick Up Kits for Their District | 2023-11-20 |  | 2023-11-25 |  | Leslie Caruso | CHCA President | At the end of November, the CHCA President writes a letter to the Trustees to specify when they are to pick up the assembled luminary kits for their districts. This letter can also serve as a request for confirmation of their service or their retirement as a Trustee for the upcoming year. New for 2023: This letter could be e-mailed.
112 | New Task for 2013: Organize and Implement "Call Tree" to Phone all Trustees, Reminding Them to Pick Up Kits for their District. There are 38 Districts for Luminaries. For 2023, Alan will contact Trustees for Districts #1-12; Mary Ann will contact #13-24; Adam will contact #25-40. | 2023-11-27 |  | 2023-12-01 |  | Leslie Caruso | CHCA President | During the week before the Kit Assembly Event, volunteers are assigned a list of Trustees to call. If the Trustee doesn't have a listed phone #, volunteers contact the Trustee by either e-mailing or PMing on Facebook. For 2013, the volunteers were the CHCA President, the Secretary and Eliza Thrush.
115 | New Task for 2012: Create a Facebook Event on the CHCA Facebook Page, Publicizing the Luminary Kit Assembly Event, Asking for Volunteers | 2023-11-15 |  | 2023-11-19 |  | Alan Miroslaw | CHCA President | For 2023, SignUpGenius is used for volunteers – see the Preliminary Section of this workplan.
120 | Update and Place Signage | 2023-11-24 |  | 2023-11-28 |  | Leslie Caruso | Signage Chair | No later than the beginning of the week before the Kit Assembly event, update the Luminary publicity signage for the current year's dates and any other new info. Place signage at the three main entrances to Colonial Hills: E. Selby, Indianola and Park Blvd.
130 | Update the Bundle Sheets Info, and Print a Set of Bundle Sheets | 2023-11-24 |  | 2023-12-01 |  | Will Pearce | Event Chair | No later than the week before the Kit Assembly event, update the Bundle Sheet information by copying and pasting any changed Trustee (or District) information from the (updated) Kit Assembly worksheet. Highly recommend you not try to type this info "freeform," which is susceptible to fumble-fingering! Then print a complete set of bundle sheets, and put them, along with any other supplies still at home, in the shelter house storeroom.
140 | Pick Up Keys for Shelter House and for Shelter House Storeroom | 2023-11-30 |  | 2023-11-30 |  | Will Pearce / Leslie Caruso | Event Chair / CHCA President | On the Thursday before the Friday that the pea gravel will be delivered, pick up these two keys from the CHCA President. Then go test your access on Thursday, to ensure successful tasks completion on Friday and Saturday.
150 | Receive Pea Gravel Delivery and Cover Pea Gravel with Tarps Note: For 2015, a Parks & Rec employee requested that we not cover and dump gravel on the grassy area. Thus, Chair requested the gravel be dumped on the blacktop just south of the grassy area. | 2023-12-01 |  | 2023-12-01 |  | Will Pearce | Event Chair | About an hour before the scheduled delivery of the pea gravel on Friday, cover the grassy area outside the shelter house (the grassy peninsula within the blacktop, north of the picnic table area) with blue plastic tarps from the shelter house storeroom, onto which the pea gravel will be dumped. Then, upon the arrival of the Mr. Mulch driver, direct that the pea gravel be dumped on the tarps. Then, cover the pea gravel with tarps to protect against rain or snow's further freezing the pea gravel.
160 | Move Luminary Kit Supplies into Storeroom; Also, Move into Storeroom: Napkins Sack (250), Paper Plates Package (100), Cups (100); Move Home the Box of 50 Baby Food Jars for Selby Park for Inclement Weather Contingency Note: For 2015, the store room was so congested that Chair moved only the tea light candles into it, and packed remaining supplies into car for delivery Saturday morning. | 2023-12-01 |  | 2023-12-01 |  | Will Pearce | Event Chair | On Friday, during the timeframe of the pea gravel delivery, move into the shelter house storeroom any supplies which have been purchased/donated, but are still at home. (Thus is to ensure that there will no scrambling for supplies on Saturday, and that the focus can be on execution of the Kit Assembly workplan.) Move the box of baby food jars home. New for 2022: On Friday, the Event Chair and the CHCA President set up supplies at the workstations inside the shelter house.
Kit Assembly Event Day
170 | Set Up Three Tables Outside the Shelter house for Workstations, and Tape Instructions to Tables. Note: Prior to 2011, only two tables were set up. The Event Chair observed in 2011 that three tables were necessary to maintain the rapid pace of the outside workflow. Note: For 2015, Parks & Rec purchased new, longer tables (but only 8); thus only two tables were set up outside. | 2023-12-02 | 7:45 | 2023-12-02 | 8:00 | Will Pearce | Event Chair | These two tables are located between the shoveling area and the bundling area, and are used for: a. Collection table for sacks of pea gravel b. Tables for kit assembly (where luminary components are put into the sacks of pea gravel)
175 | New Task for 2012: Pound the Six Wood Garden Stakes into the Ground at Intervals Around the Mound of Pea Gravel. Note: For 2015, the four new grocery sack racks replaced the stakes. | 2023-12-02 | 7:45 | 2023-12-02 | 8:00 | Will Pearce | Event Chair | These racks will be used to hold plastic grocery bags. Thus, a volunteer can then easily open a bag from the rack, so that the shoveler can then quickly scoop the gravel into the bag.
180 | If Not Raining or Snowing Heavily, Remove Tarps Covering the Pea Gravel | 2023-12-02 | 7:45 | 2023-12-02 | 8:00 | Will Pearce | Event Chair | Due to the expected below-freezing temperature early in the morning, the surface of the pea gravel would be frozen. Hopefully warmth and sunlight after sunrise will soon begin to thaw the surface.
190 | 2023, per COVID modifications: Detail Specifications for Setting Up Four Tables Inside the Shelter House for Reclosable Bag Luminary Components Assembly. | Each table contains: a. 2 cardboard boxes with approx. 500 tea light candles: 1 cardboard box at each of the two socially-distanced workstations per table. (However, per Task #95, Workstation #8 will have a quantity of tea light candles which equals (Total Number of Instruction Sheets - 700) * 5. b. 1000 lunch sacks (crisscrossed into groups of 5 sacks) c. 200 Luminary Kit Instruction Sheets, with 100 sheets at each of the two workstations per table (except for Workstation #8, which contains (Total Number of Sheets minus 700)(see Task #95) d. 200 reclosable plastic (freezer/refrigerator) bags (in their original cartons), with 100 bags at each of the two workstations per table (except for Workstation #8, which contains a quantity of bags which equals the (Total Number of Instruction Sheets minus 700)(see Task #95) e. At the window side (south side) of each table, the second workstation will also have its own separate receptable into which the completed kits will be put (instead of into the plastic bins described in task 210)
190 | Set Up Four Tables Inside the Shelter house for Reclosable Bag Luminary Components Assembly | 2023-12-02 | 8:00 | 2023-12-02 | 8:30 | Will Pearce | Event Chair | 2023, per COVID modifications: As explained in detail in the above COVID Modification Note, each table contains the quantities of candles, lunch sacks and reclosable refrigerator platic bags corresponding to the number of instruction sheets at each workstation (also see task 95).
200 | Working from a Bundle of 500 Lunch Sacks, Count Out and Crisscross the Lunch Sacks Into Groups of Five Sacks | 2023-12-02 | 8:30 | 2023-12-02 | 9:30 | Will Pearce/ Early Arriving Volunteers | Event Chair | This task enables focused and high quality performance of the subsequent workflow of assembling the luminary kit components into the reclosable plastic bags. In the past, this task has been performed by early arriving volunteers (in the 8:30 to 9:30 timeframe). Optional, starting 2011: Event Chair performs this task at home prior to Event Day.
210 | Set Up Two Tables Inside the Shelter House Beside the Above Four Tables | 2023-12-02 | 8:30 | 2023-12-02 | 8:35 | Will Pearce | Event Chair | Each table will be perpendicular to, and at the end of, two of the above specified tables, and in line with the east side shelter house door. On each of these tables will be placed a large plastic bin from the storeroom, into which will be put the closed reclosable bags containing the assembled luminary kit components (5 candles, 5 lunch sacks and 1 instruction sheet). When the bins are full, they will be carried outside, and the reclosable bags will be put on an outside table.
220 | Make the Box of Plastic Grocery Sacks and the Grocery Sack Racks Available to the First Shoveling Volunteer Note: For 2015, this task was updated to add to it the text "and the Grocery Sack Racks." | 2023-12-02 | 9:00 | 2023-12-02 | 9:15 | Will Pearce | Event Chair | This task is not performed until around 9:00 to 9:15 A.M., when there may be more volunteers present in the area, so that the grocery sacks have no chance of "vanishing"; rather, the box of grocery sacks (and the racks) will be given to the first shoveling volunteer who will start setting up the shoveling stations.
225 | New Task for 2013: Set Out the CHCA Event Form, for the Youth Volunteers to Sign | 2023-12-02 | 9:00 | 2023-12-02 | 9:05 | Will Pearce | Event Chair | The youth volunteers sign this form to obtain credits toward their CHCA Senior Scholarship eligibility. The form is incorporated into the Event Report submitted to the CHCA President, and is submitted to the VP/Events, who maintains this information.
230 | Bring and Set Up Coffee and Donuts, etc. (The Event Chair is Responsible for Inventorying/Procuring Required Paper Plates, Cups and Napkins -- See the Above Task for Moving Supplies into the Shelter House) Note for 2017: In addition to contacting Tim Horton's the Friday before Event Day, it is suggested the volunteer call them on Saturday morning about 1/2 hour before arrival to make sure they are working on the order. Note for 2021: Replaced Tim Horton's with Dunkin' Donuts, Linworth. | 2023-12-02 | 9:00 | 2023-12-02 | 9:30 | Mary Ann Ogle | Event Chair | This is a special volunteer for this event, who needs to be recruited in advance. Due to time constraints this should be a different person from the Event Chair. The quantities of victuals that we have made available are: - 1 carton coffee (regular, not decaf) (For 2012, most of the 2 cartons was not drunk; thus only 1 carton is specified for 2013.) - 1 carton hot chocolate - 3 dozen donuts (1 dozen glazed, 2 dozen assorted) - 1 dozen muffins - 1 dozen cream cheese packages
240 | Give Instructions for Any Early Arriving Volunteers | 2023-12-02 | 8:30 | 2023-12-02 | 9:45 | Will Pearce / Early-Arriving Volunteers | Event Chair | The Event Chair instructs the early arriving (8:30 to around 9:45) volunteers in the workflow task that the volunteer wishes to perform; in turn, the early-arriving volunteers instruct the rest of the volunteers, who fill the rest of the workstations. Instructions are given for: - Inside luminary components kit assembly (candles & lunch bags into reclosable plastic bags) - Pea gravel shoveling - Outside kit assembly - Kits bundling
250 | Begin Early Workflow | 2023-12-02 | 9:30 | 2023-12-02 | 10:00 | Early-Arriving Volunteers | Event Chair | As specified in preceding tasks, the early-arriving volunteers begin the workflow, and may perform two main functions: 1) the given task at their workstation 2) instructing newly-arriving volunteers The newly-arriving volunteers in turn either fill the rest of the workstations or increase the workflow volume at a given workstation.
260 | Begin Full Workflow | 2023-12-02 | 10:00 | 2023-12-02 | 12:00 | Volunteers | Early-Arriving Volunteers / Event Chair | As specified above, by now the early-arriving volunteers are almost completely directing the workflow. As can be inferred from above, the transition from "early" to "full" workflow is hopefully dynamic and seamless; this task is listed as a separate task only because 10:00 A.M. is the advertised time for the start of the event.
270 | Begin Kits Bundling | 2023-12-02 | 9:30 | 2023-12-02 | 10:15 | Specific Volunteer: / Early-Arriving Volunteer(s) | Event Chair | This is a special task which in effect serves as process control, and determines when we are finished assembling the kits. Ideally, this specific volunteer can be recruited in advance of the event. Generally, at least one (starting in 2012, two) other volunteers assist this specific person.
280 | Monitor Workflow and Reassign Volunteers as Necessary | 2023-12-02 | 10:00 | 2023-12-02 | 12:00 | Will Pearce | Event Chair | The objective of this task is to dynamically resource and monitor the tasks such that the workflow is completed as quickly as possible; e.g., if all components have been used for a given workstation, the volunteers at that workstation, if they wish, will be asked to work at a different workstation or on a different task.
290 | Check Off Trustees as They Pick Up Their Bundle of Kits; Assist Trustees in Loading Their Kits into Their Cars | 2023-12-02 | 12:00 | 2023-12-02 | 13:00 | Specific Bundling Volunteer: "Bundling Concierge" / Additional Volunteers / Will Pearce | Event Chair | A copy of the updated KitAssembly Worksheet will be used to record when each Trustee picks up their bundle.
300 | Put Away Leftover Supplies in the Storeroom, and Clean and Sweep Shelter house | 2023-12-02 | 13:00 | 2023-12-02 | 14:00 | Will Pearce / Volunteers | Event Chair | The leftover supplies are put back into the northeast corner of the storeroom, per the sign on the wall there.
310 | Dispose of Any Leftover Pea Gravel; Clean Off, Fold and Put Tarps Back into Storeroom | 2023-12-02 | 13:00 | 2023-12-02 | 14:00 | Will Pearce / Volunteers | Event Chair | The VP/Events is asked to post on the FB pages that leftover pea gravel is available for free, for residents to take.
320 | Deliver Kits to Any Trustees Who Aren't Able to Pick Up Their Kits | 2023-12-02 | 13:00 | 2023-12-02 | 15:00 | Will Pearce / Volunteers | Event Chair | Around 1:00 P.M., for any Trustees who have not yet picked up their kits, or who had previously notified us that they wouldn't be able to pick up their kits, the Event Chair and volunteers will start to deliver the Trustee's bundle of kits to the given Trustee(s).
*** End of Kit Assembly Event-Day Tasks ***
324 | New Task for 2014: Place the (Painted) Luminary Night Event Signage | 2023-12-04 |  | 2023-12-05 |  | Leslie Caruso | Signage Chair | About 5 days before the Sunday Luminary Night, the Signage Chair will retrieve this signage from the shelter house storeroom, and place one sign at each of the three main entrances to Colonial Hills: E. Selby (across from St. Michael), Indianola and Park Blvd.
330 | Assemble the Selby Park Luminaries, and Put into Boxes for Convenient Carrying | 2023-12-07 | 15:00 | 2023-12-10 | 17:30 | Will Pearce | Event Chair | The Event Chair will store the ten Selby Park luminary kits at home. No later than the Sunday when the luminaries will be lit, the Event Chair will set up the 50 luminaries from these kits, and place the luminaries in boxes for convenient transportation to Selby Park. Optional, starting 2012: Per discussion at the January, 2012 CHCA Mtg, the Event Chair may substitute longer-burning white votive candles (which burn for approximately 8 hours, and will be purchased along w/ the tea light candles), for the 50 tea light candles in the kits. (Event Chair has donated cost for these candles each year.) Note: If inclement weather is expected, the luminary kits will be set up using the baby food jars which are saved for this purpose in the shelter house storeroom.
340 | Place the Luminaries Around Selby Park and Light Them | 2023-12-10 | 17:30 | 2023-12-10 | 19:00 | Will Pearce / Volunteers | Event Chair | Starting around 5:30 P.M. on Sunday, these luminaries will be spaced approximately equidistant around the perimeter. Then the luminaries will be lit starting at approximately 6:15 P.M., such that all will be lit by 7:00 P.M. Note: Much more efficient to light the luminaries in their carrying boxes inside the garage than outside in situ.
350 | Note: At the October, 2017, CHCA meeting we decided not to perform this task for 2017. Open the Shelter House, Provide Hot Cocoa and Host Luminary Lighting Colonial Hills Get Together, at 6:00 P.M. (Changed from 7:00 to 6:00 PM for 2013.) | 2023-12-10 | 19:00 | 2023-12-10 | 20:00 | Leslie Caruso | CHCA President | This is an optional task, to be directed by the CHCA President and Officers as desired for the given year. This task is included in this Workplan due to its importance to the Colonial Hills community in maximizing the enjoyment of the luminary display and of the season, but is not part of the luminary display workflow, per se (for which the Event Chair is responsible).
354 | 2017 Note: See task 350. In conjunction with lighting the luminaries, groups (such as a group of boy or girl scouts, choir, band or just festively-inspired neighbors) will carol in the Colonial Hills neighborhood, starting after the luminaries are lit, fortified by victuals in the shelter house, around 7:00 P.M. | 2023-12-10 | 19:00 | 2023-12-10 | 20:00 | Leslie Caruso | CHCA President | This is an optional task, to be directed by the CHCA President and Officers as desired for the given year. This task is included in this Workplan due to its importance to the Colonial Hills community in maximizing the enjoyment of the luminary display and of the season, but is not part of the luminary display workflow, per se (for which the Event Chair is responsible).
360 | Pick Up and Throw Away the Luminaries Surrounding Selby Park | 2023-12-11 |  | 2023-12-11 |  | Will Pearce | Event Chair | This is a housekeeping task for Selby Park, and should be done no later than the afternoon of the Monday following the luminary display. Update, 12/19/2011: This task needs to be done by early Monday morning, to preclude the possibility of Parks & Rec's disposing of any baby food jars in the luminary lunch sacks during their trash pickup for Selby Park.
370 | Write Letter for Publication in the Next Courier, Thanking Any Vendors Who Donated Luminary Supplies | 2023-12-20 |  | 2023-12-31 |  | Will Pearce | Event Chair | This task should be submitted to the CHCA President / Courier Editor, no later than the last week of December, such that this article can appear in the January Courier.
380 | Hand Carry a Copy of the Courier Which Contains Their Thank-You Article to Any Vendor Who Donated Supplies, and Personally Thank the Vendor's Manager That Provided the Supplies | 2024-01-18 |  | 2024-01-31 |  | Will Pearce | Event Chair | This task should be performed in January, such that the vendor is thanked in a timely manner, and will see the favorable publicity that ensued from their generous gift to the CHCA.
*** End of Event Workplan ***